## Sheet1
Example RACI chart for NCRA work
| Main Role associated with tasks | Country's Minister with responsibilities for Cyber Security |  |  |  |  | Department Head for Cyber Security aka NCRA Sponsor |  |  |  | Country's NCRA Team Lead |  |  |  |  | CNI Sector Liaison |  |  | NCRA Results Presenter |  |  |  | NCRA Events Organiser |  |  | Cyber Expert for CNI |  | NCRA Data Analyser
| Main responsibilities (others may need to be defined) | Provide permission for the NCRA | Ensure resources assigned for NCRA | Champion cyber at national level | Encourage CEOs of CNI organisations | Report NCRA findings to cabinet colleagues | Set & enforce standards for NCRA | Scope the NCRA | Manage resources for NCRA | Champion the NCRA. | Plan the NCRA | Manage NCRA tasks | Ensure final NCRA data quality | Ensure NCRA data security | Ensure resolution of NCRA risks & issues | Maintain good relations with CNI system owners | Facilitate NCRA findings with CNI system representatives | Act as conduit for improving critical system data quality | Pull together NCRA reports & presentations | Ensure reports are accurate & publishable | Present findings to the CNI representatives | Manage CNI representatives' questions | Find & secure venues for NCRA workshops | Manage attendee logistics for workshops | Provide refreshments and materials for attendees | Provide NCRA recommendations | Quality Assure NCRA responses | Quality assure data completeness | Tailor NCRA spreadsheets | Do data entry / data aggregation | Export tables, graphs and charts
Name of NCRA team member | Job
Replace with Name of Person 1 | Minister | A/R | A | A/R | A/R | A/R | C | I | C | C | I | I | I | I |  | I |  |  | I |  | C
Replace with Name of Person 2 | Department Head |  |  | C | C | C | A/R | A/R | A | A/R | C | I | I | I | I | C | C | C | C | C | C | C | I | I | I | C/I | I
Replace with Name of Person 3 | NCRA Team Lead | [5 empty] | C | C | C | C | A/R | A/R | A/R | A/R | A/R | A/C | A/C | A/C | A/C | A/C | A/C | A/C | A/C | A/C | A/I | A/R | A/R | A/I | A/I | A/I | A/I
Replace with Name of Person 4 | Liaison - Government | [11 empty] | C | C | C | R | R | R |  | C | C | C |  |  |  | C | C/I | C/I |  |  |  | C = Contributes: Multiple people possible
Replace with Name of Person 5 | Liaison - Financial Services | [11 empty] | C | C | C | R | R | R |  | C | C | C |  |  |  | C | C/I | C/I |  |  |  | C = Contributes: Multiple people possible
Replace with Name of Person 6 | Liaison - Energy | [11 empty] | C | C | C | R | R | R |  | C | C | C |  |  |  | C | C/I | C/I |  |  |  | C = Contributes: Multiple people possible
Replace with Name of Person 7 | Liaison - Telecoms | [11 empty] | C | C | C | R | R | R |  | C | C | C |  |  |  | C | C/I | C/I |  |  |  | I = Informed: Multiple people possible: Identifies who must be kept informed - some nay be very influencial!
Replace with Name of Person 8 | Liaison - Another sector | [11 empty] | C | C | C | R | R | R |  | C | C | C |  |  |  | C | C/I | C/I
Replace with Name of Person 9 | Events organiser | [21 empty] | R | R | R
Replace with Name of Person 10 | Cyber Expert - Telecom systems | [24 empty] | R | R
Replace with Name of Person 11 | Cyber Expert - Financial systems | [24 empty] | R | R
Replace with Name of Person 12 | Cyber Expert - General | [24 empty] | R | R
Replace with Name of Person 13 | Results presenter (often Team Lead) | [17 empty] | R | R | R | R
Replace with Name of Person 14 | Data Analyser | [26 empty] | R | R | R | R
Replace with Name of Person 15 | Data Analyser - support | [26 empty] | C | C | C | C
Note: Rows for additional team members have been hidden |  | R = Responsible: Multiple people possible: Identifies who is majorly tasked with DOING the work
A = Accountable: Only one possible per responsibility: identifies who the buck stops with!
C = Contributes: Multiple people possible: Identifies support / helpers - some may be very influencial!
I = Informed: Multiple people possible: Identifies who MUST be kept informed - some may be very influencial!